## User Registeration
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
1 | Open | Muhammed Mondy | v1.0 | TC04 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: '123ali'. 5. Enter a valid email. 6. Click on SignUp Button. | An error message "Name Shouldn't Start With Number". | Name field accepts names starting with numbers. | High | Major
2 | Open | Muhammed Mondy | v1.0 | TC05 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'ali123'. 5. Enter a valid email. 6. Click on SignUp Button. | An error message "Name Shouldn't End With Number". | Name field accepts names ending with numbers. | High | Major
3 | Open | Muhammed Mondy | v1.0 | TC06 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'Khalid Eisadfsdfjksnfkjnsdfjksdfkjns'. 5. Enter a valid email. 6. Click on SignUp Button. | An error message "Name Shouldn't be more than 25 characters". | Name field accepts more than 25 characters. | High | Major
4 | Open | Muhammed Mondy | v1.0 | TC07 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: ' ali mohamed'. 5. Enter a valid email. 6. Click on SignUp Button. | An error message "First Character Shouldn't be a space". | Name field accepts names starting with spaces. | High | Major
5 | Open | Muhammed Mondy | v1.0 | TC12 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'ValidName'. 5. Enter in the email field: 'invalidmailexample'. 6. Click on SignUp Button. | An error message "The Email Must Contain a Domain". | Email field accepts emails without a domain. | High | Major
6 | Open | Muhammed Mondy | v1.0 | TC14 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'ValidName'. 5. Enter in the email field: 'valid!*@example.com'. 6. Click on SignUp Button. | An error message "The Email Mustn't Contain Special Characters". | Email field accepts emails with special characters. | High | Major
7 | Open | Muhammed Mondy | v1.0 | TC15 | 1. Launch the browser. 2. Go to https://automationexercise.com/. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'ValidName'. 5. Enter in the email field: 'valid @example.com'. 6. Click on SignUp Button. | An error message "The Email Mustn't Contain Spaces". | Email field accepts emails with spaces. | High | Major
8 | Open | Muhammed Mondy | v1.0 | TC16 | 1. Navigate to the registration page. 2. Click on the Country dropdown. | The dropdown should display all available countries without any missing entries. | The dropdown doesn't display all available countries. | High | Major
9 | Open | Muhammed Mondy | v1.0 | TC20 | 1. Navigate to the registration page. 2. Enter an invalid Zip Code (e.g., 'ABCDE'). | The Zip Code field should display an error message for invalid input. | The Zip Code field accepts invalid Zip Codes. | High | Major
10 | Open | Muhammed Mondy | v1.0 | TC23 | 1. Navigate to the registration page. 2. Enter an invalid Egyptian Mobile Number (e.g., '20123'). | The Mobile Number field should display an error message for invalid input. | The Mobile Number field accepts invalid numbers. | High | Major

## Login
Defect # | Status | Raised By | Tested on Version | Test Case ID | Steps to Reproduce | Expected Result | Actual Result | Priority | Severity
1 | Open | Muhammed Ayman | v1.0 | TC_004 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'user!@#'. 5. Enter email: 'test@example.com'. 6. Click on SignUp Button. | An error message is displayed: "Invalid username format." | No error message is displayed. | High | Major
2 | Open | Muhammed Ayman | v1.0 | TC_006 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'User Name'. 5. Enter email: 'test@example.com'. 6. Click on SignUp Button. | An error message is displayed: "Username cannot contain spaces." | No error message is displayed. | High | Major
3 | Open | Muhammed Ayman | v1.0 | TC_008 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'user12345678901234567890'. 5. Enter email: 'test@example.com'. 6. Click on SignUp Button. | An error message is displayed: "Username must not exceed X characters." | No error message is displayed. | High | Major
4 | Open | Muhammed Ayman | v1.0 | TC_009 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'UserName'. 5. Enter email: 'test@exampletoolongemailaddress.com'. 6. Click on SignUp Button. | An error message is displayed: "Email must not exceed X characters." | No error message is displayed. | High | Major
5 | Open | Muhammed Ayman | v1.0 | TC_010 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'UserNAme'. 5. Enter email: 'test@example.com'. 6. Click on SignUp Button. | Login is successful if the username is case-sensitive; otherwise, an error message is displayed. | An error message is displayed. | Medium | Minor
6 | Open | Muhammed Ayman | v1.0 | TC_012 | 1. Launch the browser. 2. Go to 'https://automationexercise.com/'. 3. Click on 'Signup / Login' on the Navbar. 4. Enter in the name field: 'wronguser'. 5. Enter email: 'test@example.com'. 6. Click on SignUp Button. | An error message is displayed: "Invalid username." | No error message is displayed. | High | Major